## DV_Plan_FIFO
Category	Owners		N# Asssumes	N# Assertions	N# Covers	N# Total	Status
assertion	Joanna/ Ana		0	0	0	0	TBD	Any code done yet
assumes	Joanna/ Ana		0	1	0	1	CODED	This attribute has some of code
cover	Joanna/ Ana		4	19	9	32	PASS	This attribute seems to work correctly
			0	0	4	4	CEX	COUNTER EXAMPLE
			4	20	13	37

	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	full_not_write_en	assertion	Joanna	Joanna	PASS	The property assures that if FIFO is full then write enable signal must not be active.
	2	empty_not_read_en	assertion	Joanna	Joanna	PASS	The property assures that if FIFO is empty then read enable signal must not be active.
	3	wr_ptr_increm_write_en_on	assertion	Joanna	Joanna	PASS	The property assures that write pointer increments when a write operation happen
	4	rd_ptr_increm_rd_en_on	assertion	Joanna	Joanna	PASS	The property assures that read pointer increments when a read operation happen.
	5	wr_ptr_next_increm_write_en_on	assertion	Joanna	Joanna	PASS	The property assures that wrPtrNext increments when a write operation happen
	6	rd_ptr_next_increm_rd_en_on	assertion	Joanna	Joanna	PASS	The property assures that rdPtrNext increments when a read operation happen.
	7	wr_en_off_wr_ptr_stable	assertion	Joanna	Ana	PASS	The property assures that wrPtr is stable if a write doesn't occur.
	8	rd_en_off_rd_ptr_stable	assertion	Joanna	Ana	PASS	The property assures that rdPtr is stable if a read doesn't occur.
	9	rst_rd_ptr_wr_ptr_zero	assertion	Joanna	Joanna	PASS	After reset the read and write pointers must have the same value and be 0
	10	rst_readEnOff_until_writeEn_on	assertion	Joanna	Joanna	CODED	After reset is active read enable is off until a write operation happens.
	11	never_full_and_empty	assertion	Joanna	Ana	PASS	The full and empty flags can never be active at the same time.
	12	wr_ptr_next_maxvalue_reset0	assertion	Joanna	Ana	PASS	When wrPtrNext reaches max value wraps around to 0
	13	rd_ptr_next_maxvalue_reset0	assertion	Joanna	Ana	PASS	When rdPtrNext reaches max value wraps around to 0
	14	wr_ptr_maxvalue_reset0	assertion	Joanna	Ana	PASS	When wrPtr reaches max value wraps around to 0
	15	rd_ptr_maxvalue_reset0	assertion	Joanna	Ana	PASS	When rdPtr reaches max value wraps around to 0
	16	empty_on_whenreset	assertion	Joanna	Ana	PASS	Empty signal active when reset
	17	full_off_whenreset	assertion	Joanna	Ana	PASS	Full signal off when reset
	18	write_correctly	assertion	Joanna	Joanna	PASS	This property verifies that writeData was writen correctly when the writeEn is activated
	19	read_correctly	assertion	Joanna	Joanna	PASS	This property verifies that readData was read correctly when readEn is activated
	20	fifo_stable_when_write_enoff	assertion	Joanna	Joanna	PASS	The property assures that FIFO memory value is stable if writeEn is not active
	1	write_enoff_rst_on	assumes	Joanna	Joanna	PASS	Assume write enable is not active when rst = 1
	2	read_enoff_rst_on	assumes	Joanna	Joanna	PASS	Assume read enable is not active when rst = 1
	3	read_enoff_empty	assumes	Joanna	Joanna	PASS	Assume read enable is not active when empty is active
	4	writ_enoff_full	assumes	Joanna	Joanna	PASS	Assume write enable is not active when full is active
	1	fifo_full	cover	Joanna	Joanna	PASS	Cover that the FIFO becomes full
	2	fifo_empty	cover	Joanna	Joanna	PASS	Cover that the FIFO becomes empty
	3	fifo_notfull	cover	Joanna	Joanna	PASS	Cover that the write enable signal is asserted when the FIFO is not full
	4	fifo_notempty	cover	Joanna	Joanna	PASS	Cover that the read enable signal is asserted when the FIFO is not empty
	5	write_all_address	cover	Joanna	Ana	PASS	All the memory was written
	6	read_all_address	cover	Joanna	Ana	PASS	All the memory was read
	7	write_en_fifo_full	cover	Joanna	Joanna	CEX	What if writeEn is active while FIFO is full.	se van a cambiar a acersiones en un top level
	8	read_en_fifo_empty	cover	Joanna	Joanna	CEX	What if readEn is active while FIFO is empty.
	9	write_and_read	cover	Joanna	Joanna	PASS	Read and write at the same time.
	10	write_and_read_mem_full	cover	Joanna	Ana	CEX	Read and write at the same time while the memory is full.
	11	write_and_read_mem_empty	cover	Joanna	Ana	CEX	Read and write at the same time while the memory is empty.
	12	fifo_full_no_full	cover	Joanna	Ana	PASS	Cover a sequence when FIFO becomes full and then no full
	13	fifo_empty_no_empty	cover	Joanna	Ana	PASS	Cover a sequence when FIFO becomes empty and then no empty

							To do list:
							Have specific testcases and constrains to test in Formal Verification tool.
							Based on the DV Plan, can we justify that the first data to enter into de memory is the first to come out? the order is correct?
							if the write pointer is smaller than the read pointer, in the next posedge of the clock can the write pointer be bigger than the read pointer?

	TABLES BY CONFIG
	Depth 8 DataWidth 32								ALL CONFIGS TABLE

	N # Assertion	Time	Bound		N # Cover	Time	Bound			Memory Config	Average Time Assetion			Memory Config	Average Time Cover
	1	0.00	Infinite		1	0.00	2 - 10			8 x 32	0.00			8 x 32	0.00
	2	0.00	Infinite		2	0.00	1			128 x 64	3.34			128 x 64	1.26
	3	0.00	Infinite		3	0.00	2			256 x 64	10.50			256 x 64	19.73
	4	0.00	Infinite		4	0.00	2 - 3			1k x 64	29.76			1k x 64	8.68
	5	0.00	Infinite		5	0.00	2			4k x 64				4k x 64
	6	0.00	Infinite		6	0.00	2 - 3			16k x 64				16k x 64
	7	0.00	Infinite		7	0.00	Infinite
	8	0.00	Infinite		8	0.00	Infinite		'Average Time Assetion' / Memory Configuration / Average Time Assetion					'Average Time Assetion' / Memory Configuration / Average Time Assetion
	9	0.00	Infinite		9	0.00	2 - 3
					10	0.00	Infinite
	11	0.00	Infinite		11	0.00	Infinite
	12	0.00	Infinite		12	0.00	11
	13	0.00	Infinite		13	0.00	2 - 4
	14	0.00	Infinite
	15	0.00	Infinite
	16	0.00	Infinite
	17	0.00	Infinite
	18	0.00	Infinite
	19	0.00	Infinite
	20	0.00	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	128 X 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0.00	Infinite			1	6.20	41 - 130
	2	0.00	Infinite			2	0.00	1
	3	0.00	Infinite			3	0.20	2
	4	0.10	Infinite			4	0.30	3
	5	0.60	Infinite			5	0.20	2
	6	0.60	Infinite			6	0.30	3
	7	0.00	Infinite			7	0.00	Infinite
	8	0.00	Infinite			8	0.00	Infinite
	9	0.20	Infinite			9	0.30	3
						10	1.50	Infinite
	11	0.00	Infinite			11	1.50	Infinite
	12	0.00	Infinite			12	5.50	131
	13	0.00	Infinite			13	0.40	4
	14	2.90	Infinite
	15	3.00	Infinite
	16	0.20	Infinite
	17	0.20	Infinite
	18	27.10	Infinite
	19	1.50	Infinite
	20	27.10	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	256 X 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0.00	Infinite			1	125.70	258
	2	0.00	Infinite			2	0.00	1
	3	0.10	Infinite			3	0.20	2
	4	0.10	Infinite			4	0.50	3
	5	1.60	Infinite			5	0.40	2
	6	1.80	Infinite			6	0.60	3
	7	0.10	Infinite			7	0.00	Infinite
	8	0.10	Infinite			8	0.00	Infinite
	9	0.30	Infinite			9	0.70	3
						10	0.80	Infinite
	11	0.00	Infinite			11	0.80	Infinite
	12	0.10	Infinite			12	126.00	259
	13	0.10	Infinite			13	0.80	4
	14	0.10	Infinite
	15	0.10	Infinite
	16	0.30	Infinite
	17	0.30	Infinite
	18	94.60	Infinite
	19	5.20	Infinite
	20	94.60	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	1k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0.00	Infinite			1	47.10	46 - 1026
	2	0.00	Infinite			2	0.00	1
	3	0.30	Infinite			3	0.50	2
	4	0.50	Infinite			4	1.40	3
	5	0.30	Infinite			5	0.50	2
	6	0.00	Infinite			6	1.80	3
	7	0.30	Infinite			7	0.00	Infinite
	8	0.30	Infinite			8	0.00	Infinite
	9	2.20	Infinite			9	1.80	3
						10	5.20	Infinite
	11	0.00	Infinite			11	5.20	Infinite
	12	0.30	Infinite			12	47.10	1027
	13	0.30	Infinite			13	2.30	4
	14	0.30	Infinite
	15	0.40	Infinite
	16	2.20	Infinite
	17	2.20	Infinite
	18	178.70	Infinite
	19	23.90	Infinite
	20	353.20	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	4k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1		Infinite			1		1
	2		Infinite			2		1
	3		Infinite			3		2
	4		Infinite			4		3
	5		Infinite			5		2
	6		Infinite			6		3
	7		Infinite			7		Infinite
	8		Infinite			8		Infinite
	9		Infinite			9		3
						10		Infinite
	11		Infinite			11		Infinite
	12		Infinite			12		1
	13		Infinite			13		4
	14		Infinite
	15		Infinite
	16		Infinite
	17		Infinite
	18		Infinite
	19		Infinite
	20		Infinite

	16k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1		Infinite			1		1
	2		Infinite			2		1
	3		Infinite			3		2
	4		Infinite			4		3
	5		Infinite			5		2
	6		Infinite			6		3
	7		Infinite			7		Infinite
	8		Infinite			8		Infinite
	9		Infinite			9		3
						10		Infinite
	11		Infinite			11		Infinite
	12		Infinite			12		1
	13		Infinite			13		4
	14		Infinite
	15		Infinite
	16		Infinite
	17		Infinite
	18		Infinite
	19		Infinite
	20		Infinite

## DV_Plan_SPI_serializer
		Category	Owner	Description	Status	Number	assertion	cover	assumes
		assertion	Ana Godoy	Any code done yet	NOT STARTED	0	0	0	0
		assumes		This attribute has some of code (Not necesarily commited to Git yet)	CODED	0	0	0	0
		cover		This attribute seems to work correctly and it is already commited to Git	COMPLETED	0	0	0	0
				Working correctly 100%, already commited to Git	PASSING	32	24	7	1
				Counter example (Commited to Git)	CEX	9	9	0	0
					Total	41	33	7	1
SPI MODULE										Bitacora
N#	Name	Category	Owner	Description	Status	Comments	Planned to implement	Implemented		9-Jul
ASSUMES										Status	Comment	Status	Comment	Status	Comment
1	never_full_empty_assume	assumes	Ana Godoy	Full and Empty inputs never will assert at the same time	PASSING		25-Jun-24	25-Jun-24		PASSING					Property status 9/Jul
COVERS
1	done_flag_cover	cover	Ana Godoy	done flag was assert	PASSING		25-Jun-24	25-Jun-24		PASSING
2	state_idle_cover	cover	Ana Godoy	IDLE state ocurred	PASSING		25-Jun-24	25-Jun-24		PASSING
3	state_load_cover	cover	Ana Godoy	LOAD state ocurred	PASSING		25-Jun-24	25-Jun-24		PASSING
4	state_shift_cover	cover	Ana Godoy	SHIFT state ocurred	PASSING		25-Jun-24	25-Jun-24		PASSING
5	state_complete_cover	cover	Ana Godoy	COMPLETE state ocurred	PASSING		25-Jun-24	25-Jun-24		PASSING
6	read_en_cover	cover	Ana Godoy	read_en was assert	PASSING		25-Jun-24	25-Jun-24		PASSING
7	sclk_enable_cover	cover	Ana Godoy	sclk_enable was assert	PASSING		25-Jun-24	25-Jun-24		PASSING
ASSERTIONS
1	reset_state_value_assert	assertion	Ana Godoy	When reset the state must to be IDLE	PASSING		27-Jun-24	27-Jun-24		PASSING
2	reset_internal_signals_assert	assertion	Ana Godoy	When reset all the internal singals must to be zero	PASSING		27-Jun-24	27-Jun-24		PASSING
3	empty_reset_assert	assertion	Ana Godoy	Empty input must reset all the internal singals at the next clk posedge.	CEX	cex-vivado	25-Jun-24	25-Jun-24		CEX	Estaban mal los valores de la propiedad/Corregido
4	done_after_bitcounter_zero_assert	assertion	Ana Godoy	Done output must be activated two clock cycles after bit counter is equal to zero and state=SHIFT	CEX		25-Jun-24	25-Jun-24		CEX	No paso por el estado Complete
5	complete_state_then_done_assert	assertion	Ana Godoy	Done output must to be activated one cycle after the COMPLETE state	CEX	forward	25-Jun-24	25-Jun-24		CEX	No se activo el done
6	done_only_after_load_assert	assertion	Ana Godoy	If done is activated, the state one clock cycle before must have been COMPLETE	PASSING	reverse	25-Jun-24	25-Jun-24		PASSING
7	done_only_one_cycle_assert	assertion	Ana Godoy	Done output must remain assert for only 1 clock cycle since must be activated in the COMPLETE state and this state returns to IDLE in the next cycle without any condition.	PASSING		25-Jun-24	25-Jun-24		PASSING
8	state_after_idle_assert	assertion	Ana Godoy	IDLE state can only change to LOAD state or remain in IDLE state	PASSING	forward	25-Jun-24	25-Jun-24		PASSING
9	state_before_idle_assert	assertion	Ana Godoy	If an IDLE state ocurrs, a COMPLETE state or IDLE state or an empty or a reset must have happened one clock cycle before	CEX	reverse	27-Jun-24	27-Jun-24		CEX	Paso del estado LOAD a IDLE
10	next_state_idle_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the IDLE state	PASSING		25-Jun-24	25-Jun-24		PASSING					Assertions Status 9/Jul
11	state_after_load_assert	assertion	Ana Godoy	LOAD state must only last for one clock cycle and must always go to the SHIFT state.	PASSING	forward	25-Jun-24	25-Jun-24		PASSING
12	state_before_load_assert	assertion	Ana Godoy	If a LOAD state ocurrs, an IDLE state must have happened one clock cycle before	PASSING	reverse	27-Jun-24	27-Jun-24		PASSING
13	next_state_load_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the LOAD state	PASSING		25-Jun-24	25-Jun-24		PASSING
14	state_after_shift_assert	assertion	Ana Godoy	SHIFT state can only change to COMPLETE state or remain in SHIFT state	CEX	forward	25-Jun-24	25-Jun-24		CEX	Paso del estado SHIFT a IDLE
15	state_before_shift_assert	assertion	Ana Godoy	If a SHIFT state ocurrs a LOAD state or a SHIFT state must have happened one clock cycle before	PASSING	reverse	27-Jun-24	27-Jun-24		PASSING
16	next_state_shift_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the SHIFT state	PASSING		25-Jun-24	25-Jun-24		PASSING
17	state_after_complete_assert	assertion	Ana Godoy	COMPLETE state must only last for one clock cycle and must always go to the IDLE state.	PASSING	forward	25-Jun-24	25-Jun-24		PASSING
18	state_before_complete_assert	assertion	Ana Godoy	If a COMPLETE state ocurrs, a SHIFT state must have happened one clock cycle before	PASSING	reverse	27-Jun-24	27-Jun-24		PASSING
19	next_state_complete_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the COMPLETE state	PASSING		25-Jun-24	25-Jun-24		PASSING
20	state_idle_next_condition_assert	assertion	Ana Godoy	When the state change condition is met, the state goes from IDLE to LOAD	PASSING		25-Jun-24	25-Jun-24		PASSING
21	state_shift_next_condition_assert	assertion	Ana Godoy	When the state change condition is met, the state goes from SHIFT to COMPLETE	CEX		25-Jun-24	25-Jun-24		CEX	Paso del estado SHIFT a IDLE
22	load_state_then_read_en_assert	assertion	Ana Godoy	read_en must be asserted one clock cycle after LOAD state	PASSING	forward	25-Jun-24	25-Jun-24		PASSING
23	read_en_only_after_load_assert	assertion	Ana Godoy	If read_en is activated, the state one clock cycle before must have been LOAD	PASSING	reverse	25-Jun-24	25-Jun-24		PASSING
24	read_en_only_one_cycle_assert	assertion	Ana Godoy	read_en output must remain assert for only 1 clock cycle since must be activated in the LOAD state and this state go to SHIFT in the next cycle without any condition.	PASSING		25-Jun-24	25-Jun-24		PASSING
25	shift_reg_load_read_data_assert	assertion	Ana Godoy	The value of read_data should be assing to shift_reg in the LOAD state	CEX	cex-vivado	25-Jun-24	25-Jun-24		CEX	Paso del estado LOAD a IDLE					Covers Status 9/Jul
26	shift_state_sclk_enable_assert	assertion	Ana Godoy	sclk_enable must be asserted in the SHIFT state	PASSING	forward	25-Jun-24	25-Jun-24		PASSING
27	sclk_enable_only_shift_assert	assertion	Ana Godoy	If sclk_enable is activated, the state must be SHIFT	CEX	reverse / cex-vivado. falla porque se mantiene activo un ciclo despues del shift	26-Jun-24	26-Jun-24		CEX	sclk_enable esta encendido un ciclo de reloj durante el estado de COMPLETE
28	sclk_enableoff_sclk_stable_assert	assertion	Ana Godoy	If sclk_enable is low, sclk must be stable	PASSING		26-Jun-24	26-Jun-24		PASSING
29	clk_div_toggle_assert	assertion	Ana Godoy	clk_div must to toggle every clock cycle	PASSING		26-Jun-24	26-Jun-24		PASSING
30	sclk_toggle_enable_assert	assertion	Ana Godoy	sclk must to toggle when sclk_enable=1 and negedge of clk_div	CEX		26-Jun-24	26-Jun-24		CEX	sclk_enable dura encendido solo un ciclo y evita que sclk oscile
31	bit_counter_decrement_shift_assert	assertion	Ana Godoy	bit_counter must decrement by 1 in the SHIFT state when a negedge sclk ocurrs	PASSING		26-Jun-24	26-Jun-24		PASSING
32	mosi_bit_shift_reg_assert	assertion	Ana Godoy	Mosi signal must to have the value of the most significant bit of the shift_reg in the SHIFT state when a negedge sclk ocurrs	PASSING		26-Jun-24	26-Jun-24		PASSING
33	shift_left_mult_2_assert	assertion	Ana Godoy	Shift-left operation is equivalent to multiplying by 2, therefore when shifting the register we must obtain the same register multiplied by 2	PASSING		27-Jun-24	27-Jun-24		PASSING
34		assertion	Ana Godoy

														Status	Type	Name	Engine	Bound	Trace	Time
														Resultados de correr las propiedades en el TOP 8/jul
														✓	Assert	state_shift_next_condition_assert	AGcustom11(2299)	Infinite	0	52.8
														✓	Assert	state_idle_next_condition_assert	Mpcustom4(1)	Infinite	0	3.6
														✓	Assert	state_before_shift_assert	Mpcustom4(1)	Infinite	0	3.5
														✓	Assert	state_before_load_assert	Mpcustom4(1)	Infinite	0	3.5
														✓	Assert	state_before_complete_assert	Mpcustom4(1)	Infinite	0	3.6
														✓	Assert	state_after_load_assert	Mpcustom4(154)	Infinite	0	425.5
														✓	Assert	state_after_idle_assert	Oh(1)	Infinite	0	1.5
														✓	Assert	state_after_complete_assert	Mpcustom4(1)	Infinite	0	3.5
														✓	Assert	shift_state_sclk_enable_assert	Mpcustom4(1)	Infinite	0	3.7
														✓	Assert	shift_left_mult_2_assert	AM(10)	Infinite	0	0.1
														✓	Assert	sclk_enableoff_sclk_stable_assert	PRE	Infinite	0	0.0
														✓	Assert	reset_state_value_assert	PRE	Infinite	0	0.0
														✓	Assert	reset_internal_signals_assert	PRE	Infinite	0	0.0
														✓	Assert	read_en_only_one_cycle_assert	Oh(1)	Infinite	0	1.5
														✓	Assert	read_en_only_after_load_assert	PRE	Infinite	0	0.0
														✓	Assert	next_state_shift_assert	PRE	Infinite	0	0.0
														✓	Assert	next_state_load_assert	Hp(1)	Infinite	0	1.5
														✓	Assert	next_state_idle_assert	PRE	Infinite	0	0.0
														✓	Assert	next_state_complete_assert	Hp(1)	Infinite	0	1.6
														✓	Assert	mosi_bit_shift_reg_assert	AM(10)	Infinite	0	0.0
														✓	Assert	load_state_then_read_en_assert	AGcustom11(2118)	Infinite	0	17.0
														✓	Assert	done_only_one_cycle_assert	AM(8)	Infinite	0	0.0
														✓	Assert	done_only_after_load_assert	N(16)	Infinite	0	0.0
														✓	Assert	clk_div_toggle_assert	PRE	Infinite	0	0.0
														✓	Assert	bit_counter_decrement_shift_assert	AM(12)	Infinite	0	0.1
														x	Assert	state_before_idle_assert	Bm	7	1	2.3
														x	Assert	state_after_shift_assert	Bm	7	1	2.3
														x	Assert	shift_reg_load_read_data_assert	Ht	5	1	2.4
														x	Assert	sclk_toggle_enable_assert	Bm	9	1	2.4
														x	Assert	sclk_enable_only_shift_assert	B	32 - 134	1	2.0
														x	Assert	empty_reset_assert	N	2	1	0.0
														x	Assert	done_after_bitcounter_zero_assert	Gcustom9	1683 -	0	52.1
														x	Assert	complete_state_then_done_assert	Gcustom9	2347 -	0	53.0
														✓	Cover	state_SHIFT_cover	Ht	5	1	2.5
														✓	Cover	state_LOAD_cover	Ht	4	1	2.3
														✓	Cover	state_IDLE_cover	N	1	1	0.0
														✓	Cover	state_COMPLETE_cover	B	32 - 134	1	2.0
														✓	Cover	sclk_enable_cover	Ht	5	1	2.4
														✓	Cover	read_en_cover	Ht	5	1	2.4
														✓	Cover	done_flag_cover	B	32 - 135	1	2.0

														Resultados de correr las propiedades en el receptor 8/jul (faltaban algunas)
														✓	Assert	done_only_after_load_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	done_only_one_cycle_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	state_after_idle_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	next_state_idle_assert	PRE	Infinite	0	0.0
														✓	Assert	next_state_load_assert	Hp(1)	Infinite	0	0.0
														✓	Assert	next_state_shift_assert	PRE	Infinite	0	0.0
														✓	Assert	state_after_complete_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	next_state_complete_assert	Hp(1)	Infinite	0	0.0
														✓	Assert	state_idle_next_condition_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	read_en_only_after_load_assert	PRE	Infinite	0	0.0
														✓	Assert	read_en_only_one_cycle_assert	Hp(3)	Infinite	0	0.1
														✓	Assert	shift_state_sclk_enable_assert	Hp(2)	Infinite	0	0.0
														✓	Assert	sclk_enableoff_sclk_stable_assert	PRE	Infinite	0	0.0
														✓	Assert	clk_div_toggle_assert	PRE	Infinite	0	0.0
														x	Assert	empty_reset_assert	N	2	1	0.0
														x	Assert	done_after_bitcounter_zero_assert	Ht	133	1	0.2
														x	Assert	complete_state_then_done_assert	Ht	133	1	0.2
														x	Assert	state_after_load_assert	Hp	3	1	0.1
														x	Assert	state_after_shift_assert	Hp	4	1	0.2
														x	Assert	state_shift_next_condition_assert	Ht	132	1	0.2
														x	Assert	shift_reg_load_read_data_assert	Hp	3	1	0.1
														x	Assert	sclk_enable_only_shift_assert	Ht	132	1	0.2
														x	Assert	sclk_toggle_enable_assert	Hp	5	1	0.3
														✓	Cover	done_flag_cover	Ht	133	1	0.2
														✓	Cover	state_IDLE_cover	Hp	1	1	0.0
														✓	Cover	state_LOAD_cover	Hp	2	1	0.0
														✓	Cover	state_SHIFT_cover	Hp	3	1	0.1
														✓	Cover	state_COMPLETE_cover	Ht	132	1	0.2
														✓	Cover	sead_en_cover	Hp	3	1	0.1

## DV_Plan_FunctionGenerator
Category	Owners		N# Asssumes	N# Assertions	N# Covers	N# Total	Status
assertion	Joanna		Err:508	0	0	0	TBD	Any code done yet
assumes	Joanna		#REF!	8	6	25	CODED	This attribute has some of code
cover	Joanna		#REF!	0	0	0	PASS	This attribute seems to work correctly
			#REF!	0	0	0	CEX	COUNTER EXAMPLE
			Err:508	8	6	25

	funct_generator_adder
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	clrh_on_data_o_zero	assertion	Joanna	Joanna	CODED	The property assures that when clrh is high, the output data_o is set to zero.
	2	enh_on_data_o_increment	assertion	Joanna	Joanna	CODED	The property assures that when enh is high and clrh is low, the output data_o is the sum of data_a_i, data_b_i, and data_c_i.
	3	data_o_stability_when_disabled	assertion	Joanna	Joanna	CODED	The property assures that when enh is low and clrh is low, the output data_o remains unchanged.
	4	addr_increment1_when_enh	assertion	Joanna	Joanna	CODED	The property assures that when enh is active the adder adds 1 to the current addess to produce the next addess when enh is high.
	1	clrh_clears_output	cover	Joanna	Joanna	CODED	Cover that is data_o is 0 when clrh is asserted.
	2	enh_add_operation	cover	Joanna	Joanna	CODED	Cover the scenario where enh is asserted and the adder performs the addition operation.
	3	next_address_is_addr_plus_1	cover	Joanna	Joanna	CODED	Cover the scenario where enh is high, clrh is low, and addr_temp is addr + 1.
	1	enh_and_clrh_notactive_same	assumes	Joanna	Joanna	CODED	Assume enable and clear signals are not active simultaneously

							forward y reverse checkers si estas en un estado es porque se cumplieron las condiciones para transicionar
							para el estado inicial, que despues del rest la maquina de estados va a estar en un estado que yo espero
	funct_generator_fsm
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	wheidle_next_confi	assertion	Joanna	Joanna	CODED	This property assures state transition from IDLE to CONFIG when enh_conf_i is asserted.
	2	wheidle_next_gen	assertion	Joanna	Joanna	CODED	This property assures state transition from IDLE to GEN when enh_conf_i and en_low_i are not active.
	3	idle_stable	assertion	Joanna	Joanna	CODED	This property assures IDLE state is stable if enh_conf_i and en_low_i are not asserted or if a rst is active.
	4	whenconfig_next_gen	assertion	Joanna	Joanna	CODED	This property assures state transition from CONFIG to GEN when enh_conf_i and en_low_i are not active.
	5	whenconfig_next_idle	assertion	Joanna	Joanna	CODED	This property assures state transition from CONFIG to IDLE when enh_conf_i and en_low_i are not asserted
	6	whengen_next_confi	assertion	Joanna	Joanna	CODED	This property assures state transition from GEN to CONFI when enh_conf_i is asserted.
	7	whengen_next_idle	assertion	Joanna	Joanna	CODED	This property assures state transition from GEN to IDLE when enh_conf_i and en_low_i are not asserted.
	8	clrh_addr_fsm_when_idle_or_confi	assertion	Joanna	Joanna	CODED	This property assures clrh_addr_fsm should be high in IDLE or CONFI states
	9	enh_config_fsm_active_when_confi	assertion	Joanna	Joanna	CODED	This property assures enh_config_fsm should be high in CONFI state
	10	enh_gen_fsm_active_when_gen	assertion	Joanna	Joanna	CODED	This property assures enh_gen_fsm should be high in GEN state
	1	cover_state_idle	cover	Joanna	Joanna	CODED	Cover that IDLE state ocurred
	2	cover_state_confi	cover	Joanna	Joanna	CODED	Cover that CONFI state ocurred
	3	cover_state_gen	cover	Joanna	Joanna	CODED	Cover that GEN state ocurred
	4	cover_clrh_addr_fsm	cover	Joanna	Joanna	CODED	Cover that clrh_addr_fsm signal asserted
	5	cover_enh_config_fsm	cover	Joanna	Joanna	CODED	Cover that enh_config_fsm signal asserted
	6	cover_enh_gen_fsm	cover	Joanna	Joanna	CODED	Cover that enh_gen_fsm signal asserted
***********	1	initial_state_idle	assumes	Joanna	Joanna	CODED	Assume that enh_gen_fsm signal asserted

	funct_generator_multi
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	multi_cover	cover	Joanna	Joanna	CODED	Covers multiplication operation.
	1	multiplication_correct	assertion	Joanna	Joanna	CODED	The property assures when enh is active the multiplication operation performs correcty
***********	2	data_o_0_when_rst	assertion	Joanna	Joanna	CODED	The property assures that after reset data_o will be assigned the value '0.
	3	data_o_stability_when_enh_0	assertion	Joanna	Joanna	CODED	The property assures that when enh is low the output data_o remains unchanged.
***********	1	a_i _stable	assumes	Joanna	Joanna	CODED	Assume that the a_i is stable during the clock cycle.
**************	2	b_i _stable	assumes	Joanna	Joanna	CODED	Assume that the b_i is stable during the clock cycle.

	funct_generator_lut
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	read_data__o_valid	assertion	Joanna	Joanna	CODED	The property assures that the read_data_o signal does not contain any unknown values.
	2	read_addr_i_valid_range	assertion	Joanna	Joanna	CODED	The property assures that the read address (read_addr_i) is within the valid range of addresses for the LUT
	3	read_data_o_when_valid_read_addr_i	assertion	Joanna	Joanna	CODED	The property assures that if read_addr_i is valid then the read_data_o should match the value stored in lut_structure at read_addr_i
	1	cover_read_operation	cover	Joanna	Joanna	CODED	Covers that read operation occurs at least once
	2	cover_valid_output_data	cover	Joanna	Joanna	CODED	Covers that output data does not contain unknown values
	3	cover_read_add_i_incrementing	cover	Joanna	Joanna	CODED	Covers valid address increment.
	1	assume_valid_address	assumes	Joanna	Joanna	CODED	Assumes that the address provided for reading is always within the valid range.

	funct_generator_mux
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	data_o_is_data_0_i	assertion	Joanna	Joanna	CODED	The property assures data_o matches data_0_i when sel_i is 0 and enh is active.
	2	data_o_is_data_1_i	assertion	Joanna	Joanna	CODED	The property assures data_o matches data_1_i when sel_i is 1 and enh is active.
	3	data_o_is_data_2_i	assertion	Joanna	Joanna	CODED	The property assures data_o matches data_2_i when sel_i is 2 and enh is active.
	4	data_o_is_data_3_i	assertion	Joanna	Joanna	CODED	The property assures data_o matches data_3_i when sel_i is 3 and enh is active.
	1	cover_enh_1_sel_0	cover	Joanna	Joanna	CODED	Covers when enable is active and selector value is 0.
	2	cover_enh_1_sel_1	cover	Joanna	Joanna	CODED	Covers when enable is active and selector value is 1.
	3	cover_enh_1_sel_2	cover	Joanna	Joanna	CODED	Covers when enable is active and selector value is 2.
	4	cover_enh_1_sel_3	cover	Joanna	Joanna	CODED	Covers when enable is active and selector value is 3.
	1	enh_0_data_o_0	assumes	Joanna	Joanna	CODED	Assume that if ehn is not active data_o value is 0.

	funct_generator_register
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	when_rst_1_q_is_reset_value	assertion	Joanna	Joanna	CODED	The property assures that when rst is active, q should be RESET_VALUE.
	2	when_clrh_1_q_is_reset_value	assertion	Joanna	Joanna	CODED	The property assures that when clrh is active, q should be RESET_VALUE.
	3	when_ehn_1_q_is_d	assertion	Joanna	Joanna	CODED	The property assures that when enh is active, q should be equal to d.
	4	q_holds_prev_value	assertion	Joanna	Joanna	CODED	The property assures that when neither enh, clrh, nor rst is active, q should hold its previous value.
	1	cover_rst	cover	Joanna	Joanna	CODED	Covers when rst happen.
	2	cover_clrh	cover	Joanna	Joanna	CODED	Covers when clrh happen.
	3	cover_enh	cover	Joanna	Joanna	CODED	Covers when enh happen.
	1	initial_state_is_idle	assumes	Joanna	Joanna	CODED	Assumption that the initial state is IDLE.

	funct_generator_top
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	clrh_on_addr_temp_zero	assertion	Joanna	Joanna	CODED	The property assures that when clrh is high, the output addr_temp is set to zero.
	2	addr_temp_stability_when_disabled	assertion	Joanna	Joanna	CODED	The property assures that when enh is low and clrh is low, the output data_o remains unchanged.
	3	addr_increment1_when_enh	assertion	Joanna	Joanna	CODED	The property assures that when enh is active the adder adds 1 to the current addess to produce the next addess when enh is high.
	4	clrh_clears_addr_temp	cover	Joanna	Joanna	CODED	Cover that is addr_temp is 0 when clrh is asserted.
	5	next_address_is_addr_plus_1	cover	Joanna	Joanna	CODED	Cover the scenario where enh is high, clrh is low, and addr_temp is addr + 1.
	6	enh_and_clrh_notactive_same	assumes	Joanna	Joanna	CODED	Assume enable and clear signals are not active simultaneously.
	1	multiplication_correct	assertion	Joanna	Joanna	CODED	The property assures when enh_gen_fsm is active the multiplication operation performs correcty.
	2	cover_multiplication	cover	Joanna	Joanna	CODED	Cover property for the multiplication scenario.
	1	enh_config_fsm_0_when_rst	assertion	Joanna	Joanna	CODED	The property assures that after rst enh_config_fsm is 0.
	2	enh_gen_fsm_0_when_rst	assumes	Joanna	Joanna	CODED	The property assures that after rst enh_gen_fsm is 0.
	3	clrh_addr_fsm_0_when_rst	assumes	Joanna	Joanna	CODED	The property assures that after rst clrh_addr_fsm is 0.
**************	4	assert_gen_to_confi	assertion	Joanna	Joanna	CODED	The property assures GEN to CONFI transition
************	5	assert_confi_to_gen	assertion	Joanna	Joanna	CODED	The property assures CONFI to GEN transition
	6	cover_clrh_addr_fsm	assertion	Joanna	Joanna	CODED	Cover that clrh_addr_fsm signal is asserted.
	7	cover_enh_config_fsm	assertion	Joanna	Joanna	CODED	Cover that enh_config_fsm signal is asserted.
	8	cover_enh_gen_fsm	assertion	Joanna	Joanna	CODED	Cover that enh_gen_fsm signal is asserted.
	9	cover_en_low_i	assertion	Joanna	Joanna	CODED	Cover that en_low_i signal is asserted.
	10	cover_enh_conf_i	assertion	Joanna	Joanna	CODED	Cover that enh_conf_i signal is asserted.
	11		assertion	Joanna	Joanna	CODED	Cover that enh_conf_i signal is asserted.
	12		assertion	Joanna	Joanna	CODED	Cover that enh_conf_i signal is asserted.
	13		assertion	Joanna	Joanna	CODED	Cover that enh_conf_i signal is asserted.
	14		assertion	Joanna	Joanna	CODED	Cover that enh_conf_i signal is asserted.

## DV_Plan_Top
		Category	Owner	Description	Status	Number	assertion	cover	assumes
		assertion	Ana Godoy	Any code done yet	NOT STARTED	0	0	0	0
		assumes	Joanna	This attribute has some of code (Not necesarily commited to Git yet)	CODED	0	0	0	0
		cover		This attribute seems to work correctly and it is already commited to Git	COMPLETED	0	0	0	0
				Property pass, already commited to Git	PASSING	0	0	0	0
				Counter example (Commited to Git)	CEX	0	0	0	0
					Total	0	0	0	0
	TOP MODULE
N#	Name	Category	Owner	Description	Status	Comments	Planned to implement	Implemented
ASSUMES
1		assumes
2
COVERS
1		cover
2
ASSERTIONS
1		assertion
2