## DV_Plan_FIFO
Category	Owners		N# Asssumes	N# Assertions	N# Covers	N# Total	Status
assertion	Joanna/ Ana		0	0	0	0	TBD	Any code done yet
assumes	Joanna/ Ana		0	1	0	1	CODED	This attribute has some of code
cover	Joanna/ Ana		4	19	9	32	PASS	This attribute seems to work correctly
			0	0	4	4	CEX	COUNTER EXAMPLE
			4	20	13	37

	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	full_not_write_en	assertion	Joanna	Joanna	PASS	The property assures that if FIFO is full then write enable signal must not be active.
	2	empty_not_read_en	assertion	Joanna	Joanna	PASS	The property assures that if FIFO is empty then read enable signal must not be active.
	3	wr_ptr_increm_write_en_on	assertion	Joanna	Joanna	PASS	The property assures that write pointer increments when a write operation happen
	4	rd_ptr_increm_rd_en_on	assertion	Joanna	Joanna	PASS	The property assures that read pointer increments when a read operation happen.
	5	wr_ptr_next_increm_write_en_on	assertion	Joanna	Joanna	PASS	The property assures that wrPtrNext increments when a write operation happen
	6	rd_ptr_next_increm_rd_en_on	assertion	Joanna	Joanna	PASS	The property assures that rdPtrNext increments when a read operation happen.
	7	wr_en_off_wr_ptr_stable	assertion	Joanna	Ana	PASS	The property assures that wrPtr is stable if a write doesn't occur.
	8	rd_en_off_rd_ptr_stable	assertion	Joanna	Ana	PASS	The property assures that rdPtr is stable if a read doesn't occur.
	9	rst_rd_ptr_wr_ptr_zero	assertion	Joanna	Joanna	PASS	After reset the read and write pointers must have the same value and be 0
	10	rst_readEnOff_until_writeEn_on	assertion	Joanna	Joanna	CODED	After reset is active read enable is off until a write operation happens.
	11	never_full_and_empty	assertion	Joanna	Ana	PASS	The full and empty flags can never be active at the same time.
	12	wr_ptr_next_maxvalue_reset0	assertion	Joanna	Ana	PASS	When wrPtrNext reaches max value wraps around to 0
	13	rd_ptr_next_maxvalue_reset0	assertion	Joanna	Ana	PASS	When rdPtrNext reaches max value wraps around to 0
	14	wr_ptr_maxvalue_reset0	assertion	Joanna	Ana	PASS	When wrPtr reaches max value wraps around to 0
	15	rd_ptr_maxvalue_reset0	assertion	Joanna	Ana	PASS	When rdPtr reaches max value wraps around to 0
	16	empty_on_whenreset	assertion	Joanna	Ana	PASS	Empty signal active when reset
	17	full_off_whenreset	assertion	Joanna	Ana	PASS	Full signal off when reset
	18	write_correctly	assertion	Joanna	Joanna	PASS	This property verifies that writeData was writen correctly when the writeEn is activated
	19	read_correctly	assertion	Joanna	Joanna	PASS	This property verifies that readData was read correctly when readEn is activated
	20	fifo_stable_when_write_enoff	assertion	Joanna	Joanna	PASS	The property assures that FIFO memory value is stable if writeEn is not active
	1	write_enoff_rst_on	assumes	Joanna	Joanna	PASS	Assume write enable is not active when rst = 1
	2	read_enoff_rst_on	assumes	Joanna	Joanna	PASS	Assume read enable is not active when rst = 1
	3	read_enoff_empty	assumes	Joanna	Joanna	PASS	Assume read enable is not active when empty is active
	4	writ_enoff_full	assumes	Joanna	Joanna	PASS	Assume write enable is not active when full is active
	1	fifo_full	cover	Joanna	Joanna	PASS	Cover that the FIFO becomes full
	2	fifo_empty	cover	Joanna	Joanna	PASS	Cover that the FIFO becomes empty
	3	fifo_notfull	cover	Joanna	Joanna	PASS	Cover that the write enable signal is asserted when the FIFO is not full
	4	fifo_notempty	cover	Joanna	Joanna	PASS	Cover that the read enable signal is asserted when the FIFO is not empty
	5	write_all_address	cover	Joanna	Ana	PASS	All the memory was written
	6	read_all_address	cover	Joanna	Ana	PASS	All the memory was read
	7	write_en_fifo_full	cover	Joanna	Joanna	CEX	What if writeEn is active while FIFO is full.	se van a cambiar a acersiones en un top level
	8	read_en_fifo_empty	cover	Joanna	Joanna	CEX	What if readEn is active while FIFO is empty.
	9	write_and_read	cover	Joanna	Joanna	PASS	Read and write at the same time.
	10	write_and_read_mem_full	cover	Joanna	Ana	CEX	Read and write at the same time while the memory is full.
	11	write_and_read_mem_empty	cover	Joanna	Ana	CEX	Read and write at the same time while the memory is empty.
	12	fifo_full_no_full	cover	Joanna	Ana	PASS	Cover a sequence when FIFO becomes full and then no full
	13	fifo_empty_no_empty	cover	Joanna	Ana	PASS	Cover a sequence when FIFO becomes empty and then no empty

							To do list:
							Have specific testcases and constrains to test in Formal Verification tool.
							Based on the DV Plan, can we justify that the first data to enter into de memory is the first to come out? the order is correct?
							if the write pointer is smaller than the read pointer, in the next posedge of the clock can the write pointer be bigger than the read pointer?

	TABLES BY CONFIG
	Depth 8 DataWidth 32								ALL CONFIGS TABLE

	N # Assertion	Time	Bound		N # Cover	Time	Bound			Memory Config	Average Time Assetion			Memory Config	Average Time Cover
	1	0,00	Infinite		1	0,00	2 - 10			8 x 32	0,00			8 x 32	0,00
	2	0,00	Infinite		2	0,00	1			128 x 64	3,34			128 x 64	1,26
	3	0,00	Infinite		3	0,00	2			256 x 64	10,50			256 x 64	19,73
	4	0,00	Infinite		4	0,00	2 - 3			1k x 64	29,76			1k x 64	8,68
	5	0,00	Infinite		5	0,00	2			4k x 64				4k x 64
	6	0,00	Infinite		6	0,00	2 - 3			16k x 64				16k x 64
	7	0,00	Infinite		7	0,00	Infinite
	8	0,00	Infinite		8	0,00	Infinite		'Average Time Assetion' / Memory Configuration / Average Time Assetion					'Average Time Assetion' / Memory Configuration / Average Time Assetion
	9	0,00	Infinite		9	0,00	2 - 3
					10	0,00	Infinite
	11	0,00	Infinite		11	0,00	Infinite
	12	0,00	Infinite		12	0,00	11
	13	0,00	Infinite		13	0,00	2 - 4
	14	0,00	Infinite
	15	0,00	Infinite
	16	0,00	Infinite
	17	0,00	Infinite
	18	0,00	Infinite
	19	0,00	Infinite
	20	0,00	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	128 X 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0,00	Infinite			1	6,20	41 - 130
	2	0,00	Infinite			2	0,00	1
	3	0,00	Infinite			3	0,20	2
	4	0,10	Infinite			4	0,30	3
	5	0,60	Infinite			5	0,20	2
	6	0,60	Infinite			6	0,30	3
	7	0,00	Infinite			7	0,00	Infinite
	8	0,00	Infinite			8	0,00	Infinite
	9	0,20	Infinite			9	0,30	3
						10	1,50	Infinite
	11	0,00	Infinite			11	1,50	Infinite
	12	0,00	Infinite			12	5,50	131
	13	0,00	Infinite			13	0,40	4
	14	2,90	Infinite
	15	3,00	Infinite
	16	0,20	Infinite
	17	0,20	Infinite
	18	27,10	Infinite
	19	1,50	Infinite
	20	27,10	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	256 X 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0,00	Infinite			1	125,70	258
	2	0,00	Infinite			2	0,00	1
	3	0,10	Infinite			3	0,20	2
	4	0,10	Infinite			4	0,50	3
	5	1,60	Infinite			5	0,40	2
	6	1,80	Infinite			6	0,60	3
	7	0,10	Infinite			7	0,00	Infinite
	8	0,10	Infinite			8	0,00	Infinite
	9	0,30	Infinite			9	0,70	3
						10	0,80	Infinite
	11	0,00	Infinite			11	0,80	Infinite
	12	0,10	Infinite			12	126,00	259
	13	0,10	Infinite			13	0,80	4
	14	0,10	Infinite
	15	0,10	Infinite
	16	0,30	Infinite
	17	0,30	Infinite
	18	94,60	Infinite
	19	5,20	Infinite
	20	94,60	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	1k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1	0,00	Infinite			1	47,10	46 - 1026
	2	0,00	Infinite			2	0,00	1
	3	0,30	Infinite			3	0,50	2
	4	0,50	Infinite			4	1,40	3
	5	0,30	Infinite			5	0,50	2
	6	0,00	Infinite			6	1,80	3
	7	0,30	Infinite			7	0,00	Infinite
	8	0,30	Infinite			8	0,00	Infinite
	9	2,20	Infinite			9	1,80	3
						10	5,20	Infinite
	11	0,00	Infinite			11	5,20	Infinite
	12	0,30	Infinite			12	47,10	1027
	13	0,30	Infinite			13	2,30	4
	14	0,30	Infinite
	15	0,40	Infinite
	16	2,20	Infinite
	17	2,20	Infinite
	18	178,70	Infinite
	19	23,90	Infinite
	20	353,20	Infinite
Assertions / N # Assertion / Convergence Time					Covers / N # Cover / Convergence Time

	4k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1		Infinite			1		1
	2		Infinite			2		1
	3		Infinite			3		2
	4		Infinite			4		3
	5		Infinite			5		2
	6		Infinite			6		3
	7		Infinite			7		Infinite
	8		Infinite			8		Infinite
	9		Infinite			9		3
						10		Infinite
	11		Infinite			11		Infinite
	12		Infinite			12		1
	13		Infinite			13		4
	14		Infinite
	15		Infinite
	16		Infinite
	17		Infinite
	18		Infinite
	19		Infinite
	20		Infinite

	16k x 64
	N # Assertion	Time	Bound			N # Cover	Time	Bound
	1		Infinite			1		1
	2		Infinite			2		1
	3		Infinite			3		2
	4		Infinite			4		3
	5		Infinite			5		2
	6		Infinite			6		3
	7		Infinite			7		Infinite
	8		Infinite			8		Infinite
	9		Infinite			9		3
						10		Infinite
	11		Infinite			11		Infinite
	12		Infinite			12		1
	13		Infinite			13		4
	14		Infinite
	15		Infinite
	16		Infinite
	17		Infinite
	18		Infinite
	19		Infinite
	20		Infinite

## DV_Plan_SPI_serializer
		Category	Owner	Description	Status	Number	assertion	cover	assumes
		assertion	Ana Godoy	Any code done yet	NOT STARTED	0	0	0	0
		assumes		This attribute has some of code (Not necesarily commited to Git yet)	CODED	0	0	0	0
		cover		This attribute seems to work correctly and it is already commited to Git	COMPLETED	34	26	7	1
				Working correctly 100%, already commited to Git	PASSING	0	0	0	0
				Counter example (Commited to Git)	CEX	0	0	0	0
					Total	34	26	7	1
	SPI MODULE
N#	Name	Category	Owner	Description	Status	Comments	Planned to implement	Implemented
ASSUMES
1	never_full_empty_assume	assumes	Ana Godoy	Full and Empty inputs never will assert at the same time	COMPLETED		25-jun-24	25-jun-24
2
COVERS
1	done_flag_cover	cover	Ana Godoy	done flag was assert	COMPLETED		25-jun-24	25-jun-24
2	state_idle_cover	cover	Ana Godoy	IDLE state ocurred	COMPLETED		25-jun-24	25-jun-24
3	state_load_cover	cover	Ana Godoy	LOAD state ocurred	COMPLETED		25-jun-24	25-jun-24
4	state_shift_cover	cover	Ana Godoy	SHIFT state ocurred	COMPLETED		25-jun-24	25-jun-24
5	state_complete_cover	cover	Ana Godoy	COMPLETE state ocurred	COMPLETED		25-jun-24	25-jun-24
6	read_en_cover	cover	Ana Godoy	read_en was assert	COMPLETED		25-jun-24	25-jun-24
7	sclk_enable_cover	cover	Ana Godoy	sclk_enable was assert	COMPLETED		25-jun-24	25-jun-24
ASSERTIONS
1	empty_reset_assert	assertion	Ana Godoy	Empty input must reset all the internal singals at the next clk posedge.	COMPLETED	cex-vivado	25-jun-24	25-jun-24
2	done_after_bitcounter_zero_assert	assertion	Ana Godoy	Done output must be activated two clock cycles after bit counter is equal to zero and state=SHIFT	COMPLETED		25-jun-24	25-jun-24
3	complete_state_then_done_assert	assertion	Ana Godoy	Done output must to be activated one cycle after the COMPLETE state	COMPLETED	forward	25-jun-24	25-jun-24
4	done_only_after_load_assert	assertion	Ana Godoy	If done is activated, the state one clock cycle before must have been COMPLETE	COMPLETED	reverse	25-jun-24	25-jun-24
5	done_only_one_cycle_assert	assertion	Ana Godoy	Done output must remain assert for only 1 clock cycle since must be activated in the COMPLETE state and this state returns to IDLE in the next cycle without any condition.	COMPLETED		25-jun-24	25-jun-24
6	state_after_idle_assert	assertion	Ana Godoy	IDLE state can only change to LOAD state or remain in IDLE state	COMPLETED		25-jun-24	25-jun-24
7	next_state_idle_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the IDLE state	COMPLETED		25-jun-24	25-jun-24
8	state_after_load_assert	assertion	Ana Godoy	LOAD state must only last for one clock cycle and must always go to the SHIFT state.	COMPLETED		25-jun-24	25-jun-24
9	next_state_load_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the LOAD state	COMPLETED		25-jun-24	25-jun-24
10	state_after_shift_assert	assertion	Ana Godoy	SHIFT state can only change to COMPLETE state or remain in SHIFT state	COMPLETED		25-jun-24	25-jun-24
11	next_state_shift_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the SHIFT state	COMPLETED		25-jun-24	25-jun-24
12	state_after_complete_assert	assertion	Ana Godoy	COMPLETE state must only last for one clock cycle and must always go to the IDLE state.	COMPLETED		25-jun-24	25-jun-24
13	next_state_complete_assert	assertion	Ana Godoy	This property verifies that next_state signal have the correct value in the COMPLETE state	COMPLETED		25-jun-24	25-jun-24
14	state_idle_next_condition_assert	assertion	Ana Godoy	When the state change condition is met, the state goes from IDLE to LOAD	COMPLETED		25-jun-24	25-jun-24
15	state_shift_next_condition_assert	assertion	Ana Godoy	When the state change condition is met, the state goes from SHIFT to COMPLETE	COMPLETED		25-jun-24	25-jun-24
16	load_state_then_read_en_assert	assertion	Ana Godoy	read_en must be asserted one clock cycle after LOAD state	COMPLETED	forward	25-jun-24	25-jun-24
17	read_en_only_after_load_assert	assertion	Ana Godoy	If read_en is activated, the state one clock cycle before must have been LOAD	COMPLETED	reverse	25-jun-24	25-jun-24
18	read_en_only_one_cycle_assert	assertion	Ana Godoy	read_en output must remain assert for only 1 clock cycle since must be activated in the LOAD state and this state go to SHIFT in the next cycle without any condition.	COMPLETED		25-jun-24	25-jun-24
19	shift_reg_load_read_data_assert	assertion	Ana Godoy	The value of read_data should be assing to shift_reg in the LOAD state	COMPLETED	cex-vivado	25-jun-24	25-jun-24
20	shift_state_sclk_enable_assert	assertion	Ana Godoy	sclk_enable must be asserted in the SHIFT state	COMPLETED	forward	25-jun-24	25-jun-24
21	sclk_enable_only_shift_assert	assertion	Ana Godoy	If sclk_enable is activated, the state must be SHIFT	COMPLETED	reverse / cex-vivado	26-jun-24	26-jun-24
22	sclk_enableoff_sclk_stable_assert	assertion	Ana Godoy	If sclk_enable is low, sclk must be stable	COMPLETED		26-jun-24	26-jun-24
23	clk_div_toggle_assert	assertion	Ana Godoy	clk_div must to toggle every clock cycle	COMPLETED		26-jun-24	26-jun-24
24	sclk_toggle_enable_assert	assertion	Ana Godoy	sclk must to toggle when sclk_enable=1 and negedge of clk_div	COMPLETED		26-jun-24	26-jun-24
25	bit_counter_decrement_shift_assert	assertion	Ana Godoy	bit_counter must decrement by 1 in the SHIFT state when a negedge sclk ocurrs	COMPLETED		26-jun-24	26-jun-24
26	mosi_bit_shift_reg_assert	assertion	Ana Godoy	Mosi signal must to have the value of the most significant bit of the shift_reg in the SHIFT state when a negedge sclk ocurrs	COMPLETED		26-jun-24	26-jun-24
27		assertion	Ana Godoy
28		assertion	Ana Godoy

## DV_Plan_FunctionGenerator
Category	Owners		N# Asssumes	N# Assertions	N# Covers	N# Total	Status
assertion	Joanna		#¡REF!	0	0	0	TBD	Any code done yet
assumes	Joanna		#¡REF!	8	0	16	CODED	This attribute has some of code
cover	Joanna		#¡REF!	0	0	0	PASS	This attribute seems to work correctly
			#¡REF!	0	0	0	CEX	COUNTER EXAMPLE
			#¡REF!	8	0	16

	funct_generator_adder
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	clrh_on_data_o_zero	assertion	Joanna	Joanna	CODED	The property assures that when clrh is high, the output data_o is set to zero.
	2	enh_on_data_o_increment	assertion	Joanna	Joanna	CODED	The property assures that when enh is high and clrh is low, the output data_o is the sum of data_a_i, data_b_i, and data_c_i.
	3	data_o_stability_when_disabled	assertion	Joanna	Joanna	CODED	The property assures that when enh is low and clrh is low, the output data_o remains unchanged.
	4	addr_increment1_when_enh	assertion	Joanna	Joanna	CODED	The property assures that the adder adds 1 to the current addess to produce the next addess when enh is high.
	5	clrh_clears_output	cover	Joanna	Joanna	CODED	Cover that is data_o is 0 when clrh is asserted.
	6	enh_add_operation	cover	Joanna	Joanna	CODED	Cover the scenario where enh is asserted and the adder performs the addition operation.
	7	next_address_is_addr_plus_1	assertion	Joanna	Joanna	CODED	Cover the scenario where enh is high, clrh is low, and addr_temp is addr + 1.
	8	enh_and_clrh_notactive_same	assumes	Joanna	Joanna	CODED	Assume enable and clear signals are not active simultaneously

	funct_generator_multi
	N#	Name	Category	Owner	Actual Owner	Status	Description	Comments	Planned to implement	Implemented
	1	clrh_on_data_o_zero	assertion	Joanna	Joanna	CODED	The property assures that when clrh is high, the output data_o is set to zero.
	2	enh_on_data_o_increment	assertion	Joanna	Joanna	CODED	The property assures that when enh is high and clrh is low, the output data_o is the sum of data_a_i, data_b_i, and data_c_i.
	3	data_o_stability_when_disabled	assertion	Joanna	Joanna	CODED	The property assures that when enh is low and clrh is low, the output data_o remains unchanged.
	4	addr_increment1_when_enh	assertion	Joanna	Joanna	CODED	The property assures that the adder adds 1 to the current addess to produce the next addess when enh is high.
	5	clrh_clears_output	cover	Joanna	Joanna	CODED	Cover that is data_o is 0 when clrh is asserted.
	6	enh_add_operation	cover	Joanna	Joanna	CODED	Cover the scenario where enh is asserted and the adder performs the addition operation.
	7	next_address_is_addr_plus_1	assertion	Joanna	Joanna	CODED	Cover the scenario where enh is high, clrh is low, and addr_temp is addr + 1.
	8	enh_and_clrh_notactive_same	assumes	Joanna	Joanna	CODED	Assume enable and clear signals are not active simultaneously

## DV_Plan_Top
		Category	Owner	Description	Status	Number	assertion	cover	assumes
		assertion	Ana Godoy	Any code done yet	NOT STARTED	0	0	0	0
		assumes	Joanna	This attribute has some of code (Not necesarily commited to Git yet)	CODED	0	0	0	0
		cover		This attribute seems to work correctly and it is already commited to Git	COMPLETED	0	0	0	0
				Property pass, already commited to Git	PASSING	0	0	0	0
				Counter example (Commited to Git)	CEX	0	0	0	0
					Total	0	0	0	0
	TOP MODULE
N#	Name	Category	Owner	Description	Status	Comments	Planned to implement	Implemented
ASSUMES
1		assumes
2
COVERS
1		cover
2
ASSERTIONS
1		assertion
2